## Sheet1
Student Mental Health Agreement project: Monitoring progress & end of year report
Working area | Actions | Progress | Reflection | Outcome & impact
Which working area is this? This can be directly copied from your SMHA. | What actions will need to take place in order to achieve the overall aim? These bullet points can be copied from your SMHA. | An update of how this work has developed along the way. Your SMHA working group meetings should keep adding to this document as the work develops. | What has worked well and what would you do differently next year? Highlight any challenges you faced along the way. Think of opportunities for the future. Do you want to continue, refresh or stop doing this working area for next year's SMHA. | What success measure did you apply to this working area? What progress has been made towards this area? What has happened or do you expect to happen as a result of this work? How many students and/or staff have been impacted by this work and how do you know this?
1- Campaigns | 1 - Mental Health Stop the Stigma campaign – Let’s Talk 2 - Establishing a Mental Health Pledge Campaign 3 - Exam Stress Campaigns 4 - Mental Health Awareness Week 5- GCU Mental Health Campaign: GCU Community | 1 - Video produced featuring voices from sports clubs, societies, representation groups, Students' Association staff and the full time officers. Video shared and promoted using social media, GCU SA website and all student email. 2 - The GCU Mental Health Pledge Campaign was launched on the 10th of October (World Mental Health day). The pledge was created in partnership with the Students' Association, and was signed by leaders of both organisations, students and staff. The Pledge has been displayed across multiple areas on the GCU Campus, including featuring in University Mental Health Day, Time to Talk Day and more, and is currently in the Faith and Belief Centre. 3 - Stall with study and wellness materials (colouring sheets and pens/pencils, help sheets with time management activities etc.), herbal teas and biscuits/sweets as well as info on accessing support from Advice Centre and Wellbeing Team and info on mitigating circumstances was available for the full exam period in trimester A (January). In addition to this there were further digital distress activities and prompts available in the adjacent break out area encouraging breaks from study and being online. During Tri B assessment period (no exams on campus due to Covid - 19) info on Exam stress, mitigating circumstances and additional support available communicated to students via all student email and social media and GCU Learn. 4 - Events and activities planned by the Students' Association, Mental Health and Wellbeing representation group and Wellbeing Team/Student Mental Health Project Officer. Events taking place online due to Covid-19 lockdown and were promoted via social media/all student email and on GCU Learn/Blackboard. There were events for students and staff, events were: Tea Toast and chat session; Stream of Consciousness exercise; Craftercise session; Mental Health Pub Quiz; Kindness poetry Competition; Kindness Padlet; Student mindfulness session; Staff Mindfulness Session; Time to Talk event for Students, Time to Talk Event for Staff, At Home Workouts with the Arc Gym online; 25 ways to Kindness online resource. 5 - The Student Wellbeing Team has been working with students from the Design for Change module to develop a student-led awareness raising campaign (digital and print) surrounding mental health specifically to GCU. The campaign looks to take the form of a community based approach which can resonate with GCU Staff, Students, and visitors to our campus, promote an inclusive culture of openness, trust and raised awareness of mental health and wellbeing which reduces the stigma around mental health, alongside educating individuals on the GCU support available to them. | 1 -Video was recieved well, Students and SA staff very keen and willing to participate, would refresh next year with university staff included. 2- The GCU Mental Health Pledge Campaign was well received from both students and staff. The pledge allowed for a large visible presence on the campus of mental health, and empowered students and staff to consider their role in a larger community that is open and inclusive to mental health and wellbeing, and challenges stigma. The large size of the pledge also helped to direct attention to ongoing mental health events when it was present at these. The ability to move the pledge around campus was positive, as it allowed for a higher visibility by students and staff. Moving forward the pledge materials itself need to be refreshed over the summer of 2020, as due to the type of markers used the area is becoming slightly faded. 3 - Stall and break out digital detox area was successful in Tri A diet. Materials were taken and freebies went quickly! It would be good in future to have some availability of somewhere to make the hot tea nearby. The main challenge has been the fact that we are not on campus for assessments in Tri B due to Covid-19. The main elements (minus freebies) will be communicated to students via social media and all student emails. Some materials will need to be adjusted as issues causing stress will be different when assessments are online/coursework based in the main. This has been a feature of the past 2 years SMHAs and we would look to continue it next year with some developments. 4 - The individual events for students and staff to enhance wellbeing and explore different aspects of this were well received from students and staff. The online events themselves received mixed engagement, with students and staff tending to engage more with events which were on social media or Teams platforms - rather than the enrolled Course. 5- GCU Mental Health Campaign: GCU Community The campaign is currently in development with the students, who are working to refine their first draft which will then be explored through consultation with our student and staff communities, alongside key stakeholders in mental health and wellbeing who can help to ensure the messages, and shape of the campaign are ones which will resonate and educate. | 1 - Feedback was very positive-video shared via YouTube Link and social media. Number of views 48. Approx. 14 shares. Will re-run video throughout the year. 2 - The pledge has been visible and available for additional signatures to be contributed throughout the year. The ability to easily relocate the pledge has enabled it to be present at a number of wellbeing events, including Time to Talk Day, University Mental Health Day and more. All success measures were completed. 3 - Stall with info on Advice Centre and Nightline support, on Mitigating circumstances procedure and with resources (over 100 colouring sheets, pens/pencils, worksheets on resilience and stress coping strategies; Exam Stress booklets and 200 herbal teabags and 100s of packs of biscuits) was cleared out. Digital detox zone was provided during exam period in tri A. Online info and advice only in Tri B (via social media and all student emails). 4 - Activities and events planned (see progress section for full details) and also needed to be online only aligning to theme of the week; events promoted online by both SA and GCU (Including Student Life, GCU Wellbeing, Glasgow Caledonian University, Mental Health and Wellbeing Group and more) and on the wellbeing newsletter and all student emails. Event took place online 18th-24th May. An impactful outcome is following the offer of the provision of online mindfulness for staff, there has been discussions in place to begin offering this as a permanent online provision for GCU Staff due to positive participant feedback. 5- GCU Mental Health Campaign: GCU Community Although the campaign is still being developed, the initial illustrations and concept has been accepted for presentation at both the NUS Think Positive about Student Mental Health’s Scotland Conference, and at SeeMe’s ‘It Starts With You’ event. The success measures for this area are ongoing, as the campaign is continuing to be developed with our communities.
2 - Strategic Approach | 1 - QAA Cluster Project for Inclusive Curriculum Designs 2 - Project Officer for Student Mental Health 3 - Appoint two additional Counsellors in Tri A 4 - Enhance Student Mental Health Strategic Action Plan- 5 - Continue meetings of the Student Wellbeing Advisory Group 6 - Review and further enhance our Mitigating Circumstances Procedures | 1 - QAA Cluster Project for Inclusive Curriculum Designs Glasgow Caledonian University in collaboration with Heriot Watt University, University of Stirling and SPARQs are leading a project student mental wellbeing in relation to creating inclusive curricula and learning environments is a new collaborative cluster project. The project aims to develop the processes and tools that academic staff use to design curricula. This will help them create teaching and learning environments that are inclusive and promote student mental wellbeing. The project is a part of the QAA Enhancement Themes Collaborative Clusters, and has involvement from student services, academic quality, and the Students’ Association at GCU. So far, the group has hosted two professional development events which have explored this topic with staff and students across the sector on the 23rd January 2020, and the 21st May 2020 (which was converted from face to face to a webinar following Covid-19) to explore Student mental Wellbeing and Teaching during the Covid-19 Pandemic. This webinar and the keynote lecture from the event on 23rd January were delivered by Gareth Hughes, lead author of the University Mental Health Charter. 2 - Project Officer for Student Mental Health To enhance and further embed the whole institutional approach GCU undertakes in regards to enhancing our staff and student wellbeing, GCU appointed a Project Officer for Student Mental Health. The project officer’s main responsibility is to facilitate a whole institutional approach to enhancing wellbeing at GCU. 3 - Appoint two additional Counsellors in Tri A Following the announcement from the Scottish government of additional funding for counsellors across colleges and universities in Scotland, the GCU wellbeing team appointed two additional part-time counsellors in Trimester A. 4 - Enhance Student Mental Health Strategic Action Plan- In 2017, GCU introduced the development of a Student Mental Health Action Plan. We continued to enhance this action plan and further develop the ongoing work to support staff and student mental health. The action plan is overseen by our Student Wellbeing Advisory Group – which is further explored later in this document. 5 - Continue meetings of the Student Wellbeing Advisory Group The Student Wellbeing Advisory Group is a cross institutional working group and was formed in 2019 (formally the Student Mental Health Task Group) to continue working to support student mental health and wellbeing. The group features representation from across the GCU Community, including academics, GCU London, GCU Students' Association and GCU London Students' Association, INTO GCU, and a key external from the mental wellbeing sector. The group has continued to meet throughout the academic year, co-ordinate the Student Mental Health Action Plan, and contribute to ongoing work and projects across the University in relation to wellbeing. The group also provides an opportunity for colleagues across the University to focus on varying areas of wellbeing through topics for each meeting, (including International Student Wellbeing, Covid-19 Responses, GBV and more). 6 - Review and further enhance our Mitigating Circumstances Procedures Building upon prior reviews and enhancements to our Mitigating Circumstances process, we have continued this review throughout the 19/20 Academic year to explore the implementations of online submissions, alongside other amendments to the process. However, due to Covid-19 a number of changes have been immediately introduced to the process. | 1 - QAA Cluster Project for Inclusive Curriculum Designs So far the group has collected together relevant literature and research for the sector on this topic and has displayed these on their Enhancement Themes Website. The group has pulled together the event presentation, and collated participant feedback from their event on the 23rd January 2020 into an online Wakelet, and is looking to publish in the following weeks a recording of the webinar from the 21st May. The team also successfully submitted an abstract that was accepted for presentation at the forthcoming International Enhancement Themes conferences. 2 - Project Officer for Student Mental Health The position for a Project Officer for Student Mental Health was appointed in August 2020. The role has been instrumental in maintaining and enhancing a cross institutional approach by the University in regards to student and staff mental health and wellbeing. The Project Officer also looks to work collaboratively with others across the sector – including NUS Think Positive, Student Minds, SeeMe, GCU Students’ Association and SPARQs on various areas of work, and has enabled the additional introduction of a number of projects, areas of work in existing actions plans, and the evaluation of ongoing work alongside enhancing the evaluation of wellbeing service and provision at the campus. 3 - Appoint two additional Counsellors in Tri A Two positions for part time Counselling Staff were established and filled in relation to additional funding by the Scottish Government. 4 - Enhance Student Mental Health Strategic Action Plan- The Student Mental Health Action Plan is overseen and enhanced by the Student Wellbeing Advisory Group. Throughout the year, the group has actively contributed to the development and completion of actions in the plan, alongside the introduction of new areas of work. Most recently, this has included the introduction of a new area of work to explore how the institution can work to support incoming and returning students to the campus for the 2020/2021 academic year following the Covid-19 Pandemic. 5 - Continue meetings of the Student Wellbeing Advisory Group The group has continued to meet throughout the academic year and has provided a central form for the discussion of, introduction, evaluation and enhancement of projects to enhance student wellbeing. The impact of the group is further discussed in the Outcome and Impact Section, but we have found this to be an incredibly impactful group in our institution, and it was the basis of our presentation at SeeMe’s recent ‘It Starts with You’ event. We aim to continue this area of work into the upcoming Student Mental Health Agreement. 6 - Review and further enhance our Mitigating Circumstances Procedures The covid-19 situation has meant that we have streamlined our procedure and simplified this along with lessening the burden of disclosing sometimes very personal circumstances. The impact of these sudden changes will be thoroughly reviewed over the coming months. | 1 - QAA Cluster Project for Inclusive Curriculum Designs The project was successfully submitted and approved to form a Collaborative Cluster with the QAA Scotland as part of its Enhancement Themes activity, a call for others across the sector to become involved was circulated and engaged with, and the Cluster has undertaken and published their work to date. The project has successfully explored current literature on the topic of inclusivity, wellbeing and curricula and hosted two events, including interactive workshops, to engage with the sector on the theme of teaching students and impacts on their mental wellbeing. Going forward the group look to consolidate this into a report with recommendations for the sector on curricula structure and delivery, and will also explore the possibility of establishing a special interest group. The project is currently ongoing. Success measures outlined at the beginning of the Student Mental Health Agreement for this area of work have all been successfully completed. https://www.enhancementthemes.ac.uk/news-events/events/student-mental-wellbeing-and-teaching-during-the-covid-19-pandemic 2 - Project Officer for Student Mental Health The Project Officer for Student Mental Health has enhanced provisions across the University and contributed to varying areas of work across the sector. All success measures were completed. 3 - Appoint two additional Counsellors in Tri A The appointment of two additional counsellors in the first trimester following funding from the Scottish Government has enabled the Student Wellbeing Team to not only reduce their waiting list, and enhance the counselling provision of the service, but has enhanced capacity of the service to offer other wellbeing provisions, as both members of staff have actively been involved in enhancing the delivery of workshops provided by the service to students. The workshops delivered have included additional Mindfulness sessions, which have since been provided online in response to the Covid-19 Pandemic, and a seminar on Honour Based Violence (and the support available at GCU for Gender Based Violence). All success measures were completed. 4 - Enhance Student Mental Health Strategic Action Plan- The further development, completion and introduction of new working areas into the Action Plan has enabled departments from across the University and Students’ Association to explore a holistic view of the student experience in relation to wellbeing. This has allowed for projects to be included in the plan, for example Campaigns, staff development training, other ongoing work (like the Student Mental Health Agreement, and Mental Health at Work Action Plan), exploration of resources for carers, parents and others in the GCU Community, and more. This year, the plan has also embedded impact measures for each working area which are in the process of being collated and assessed. The measures enable the group to explore how impactful various areas of work have been for the GCU Community in relation to their wellbeing and how these areas of work can be further enhanced. All success measures were completed. 5 - Continue meetings of the Student Wellbeing Advisory Group The Group has continued to meet, and has met at an increased capacity this year including having extraordinary meetings to explore responses in relation to the Covid-19 Pandemic. The group has enabled a cross institutional approach in the University to explore student wellbeing, and has provided a forum for a multitude of projects and potential areas of work to be discussed, enhanced, and implemented. The group this year have also established an internal intranet site with papers, action plans, areas of work, and notable literature from the institution and sector in relation to wellbeing. All success measures were completed. 6 - Review and further enhance our Mitigating Circumstances Procedures The rapid introduction to online working and online submission of Mitigating Circumstances has forced us to quickly change our process. This will be reviewed at the end of this period and incorporate any positive changes to the process as well as barriers that student may have faced.
3 - Events | 1 - Mindful Mondays 2 - Feel Fab Feb 3 - World Mental Health Day event (Oct 10th) 4 - University Mental Health Day events (March 7th) 5 - Paws Against Stress Event 6- National Fitness Day (25th September) | 1 - Content on Mindfulness, mental health and wellbeing free apps, tips and resources shared every Monday by Students' Association Officer on social media. 2 - A month long timetable of daily events and activities organised and created by Students Association officer. More than 1 event daily Mon-Fri. Suite of events advertised using social media, all student emails, GCU comms, website, plasma screens on campus. Events took place, recorded and evaluated. 3. World Mental Health Day (10th October) On the 10th October, GCU and GCU Students’ Association held a range of activities, workshops and lectures for students and staff to enhance their health and wellbeing. This included a Tea and Talk event to raise funds for the Mental Health Foundation, a Digital Detox Zone, free Mindfulness Sessions, the opportunity to sign a Pledge for Mental Health at GCU, a fair hosted by various internal and external wellbeing organisations, and more. Wellbeing Seminars which were provided on the day were: • Lecture: Physical Activity and Mental Health by Gillian Strathearn • SAMH: Let's Talk about Mental Health and 5 Ways to Wellbeing Workshop • Feeding into GCU's work for Mental Health (Staff and Students) by Rachel Simpson, Helen Gallagher and Susan Docherty • Introduction to Mindfulness The overall objective of raising awareness of mental health issues and mobilizing efforts in support of better mental health was achieved through the delivery of these events, alongside the fair which provided internal and external support for students and staff. 4 - University Mental Health Day events (March 7th) On the 5th of March 2020 the Student Wellbeing Service worked with partners across the University and GCU Students' Association to host a range of wellbeing activities for our students and staff, Activities occurred throughout the day - including information stalls, calm zones, free tea and coffee, the mental health and wellbeing pledge, a mindful tree, wellbeing seminars and more. 5 - Paws Against Stress Event On the 14th of January 2020, the Counselling team of the Student Wellbeing Service organised for therapets and their owners to come onto campus by working with the Canine Concern Scotland Trust. https://www.canineconcernscotland.org.uk/students-and-exam-stress 6 - National Fitness Day – 25th September We recognise the link between physical activity and mental wellbeing, and the positive effects exercise can have on wellbeing and mental health. As such, GCU’s on Campus Gym (the Arc: Health and Fitness) provided free access to our on Campus Gym on National Fitness Day. | 1 - Mindful Monday was recieved very well with engagement consistent every Monday on all social media accounts; Facebook, Twitter and Instagram, shared by the Students' Association, Student Life, Mental Health and Wellbeing Group and students. Likes and comments varied each week but constant engagement and interaction on a weekly basis. 2 - Full calendar of events every week day throughout February. Students engaged with every activity. Promoted extremely well via website and social media by the Students' Association, Wellbeing, Full Time Officer team, sports clubs, societies, Student Media Groups, Mental Health and Wellbeing Group and more. Would continue event every February. Challenges were student groups wanting to add to calendar and be included after cut off date due to strong media promotion, I would promote well in advance. 3- World Mental Health Day (10th October) The variety of events which were present for students and staff throughout the day was well received by staff. The findings from the consultation event which was hosted physically and online through a Padlet have been embedded into various areas of work including the Student Mental Health Action Plan, and ongoing projects across the University. Elements of the event – including a calm zone, and mindfulness seminars were positively received by students and staff to the extent that they have been embedded into future events, including the University Mental Health Day activities. The succesful use of the Calm Zone meant we used it for exam stress campaign and helped with the creation of a quiet room/calm zone at the Students' Association. 4 - University Mental Health Day events (March 7th) The University and Students’ Association co-ordinated a range of activities across the campus (The Campus Life Lounge Seminar Rooms, Sir Alex Ferguson Library & GCU Students' Association) and enabled a several seminars, activities and student and staff consultation on proposed wellbeing projects to occur. The consultation was both physically on the campus, and mirrored online by the use of both physical papers and an online Padlet. 5 - Paws Against Stress Event The event was well attended with 51 students from across the University, and was managed through promotion on the GCU wellbeing, GCU, GCU Student life and Students’ Association Social Medias (including a Facebook Event) and an Eventbrite. 6 - National Fitness Day – 25th September Throughout the day the on campus gym was free to access to students, staff and the public. This was with the aim of engaging individuals with the gym, and promoting physical activity. There were also mental health materials throughout the campus on the day to help engage individuals with the link between mental health and physical health, and there is a close working relationship with the on campus gym provider, and the student wellbeing team. | 1 - The full time officer made at least one post per week on mindfulness and a wide variety of wellness based topics and resources that students could engage with. These were engaged with and shared weekly online and led to a regular drip feed of focus on individual wellbeing and coping strategies to improve this. 2 - A full schedule of activities for February was organised and promoted widely on campus and online. The FFF calendar online reached 1234 and 42 engaged with this . Individual posts on activities also had wide reach - e.g. Sustainable Food ABC event 951 reach and 7 responses with 30 students attending the event; Nightline Mindfulness and Meditation event reached 1103 and had 26 engagements; Paws for Stress event in February reached 3781 and had 307 engagements. Participant numbers in the individual activities are not known for all but as an example participation number 80 students attended the Paws for Stress therapets day event and 49 left feedback which was overwhelming positive.15 students took part in the Nightline Mindful meditation event (this was the capacity for the event) and also gave positive feedback. The Society and Sports events for FFF had approximately 192 participation numbers. 3. World Mental Health Day (10th October) Attendees of the event were provided with the opportunity throughout the day to complete a paper feedback form and comment on the activities of the day. Moreover, this form was circulated to any organizations/individuals who delivered talks or workshops during the day or who hosted a stall at the fayre. The variety of activities were well received, particularly the Calm Room – which featured mindful colouring and the canvas in this was noted specifically in “more canvas – they were great!”. Social media posts for the event were frequent, and the Facebook event itself reached 4,000 people, 128 responded to the event,486 click to view the event page. All success measures were achieved. 4 - University Mental Health Day events (March 7th) The feedback from the day in these consultations has been used to draft recommendations and shape ongoing work, including the proposal to introduce a Wellbeing Space to the Sir Alex Ferguson Library. The event was promoted with a Facebook Event which reached 4,300 individuals, was viewed 493 times and had 77 respondents. All success measures were achieved. 5 - Paws Against Stress Event The event was well attended and from student feedback, the benefit had a clear, positive impact on their wellbeing. The event was held during the Trimester A exam period in the Students’ Association next to the 24-hour lab, which not only allowed the therapet dogs easy access to outside grass, but enabled staff from the Student Wellbeing team to engage with students taking this 20-minute break from studying. Students tell us how much they enjoy the liveliness and uplifting nature of the event. All success measures were achieved. 6 - National Fitness Day – 25th September The event was well received by our student and staff community. We cannot get access to the system for the exact number due to home working for Covid-19, but the estimated impact was that 420 individuals accessed the gym on this day. All success measures were achieved.
4 - Workshops | 1 - Continue to offer free Mindfulness course 2 - Offering Mental Health Matters workshop at Inductions 3 -Continue to develop GCU Summer Transitions workshops 4 - Embed module on Mental Health and Wellbeing on GCU Learn 5 - Explore the possibility of a Mindfulness module at GCU 6 - Continue provision of Scottish Mental Health First Aid training to students | 1 - Continue to offer free Mindfulness course Mindfulness meditation offers simple yet powerful techniques that can be incorporated into our daily lives to help us cope with stress and increase feelings of contentment, and numerous studies have found that regular practitioners can experience a number of positive effects in their health and wellbeing. The Student Wellbeing Service has expanded their provision and now offer free mindfulness to GCU Students throughout the first and second academic trimester. 2 - Offering Mental Health Matters workshop at Inductions The Wellbeing Service introduced and delivered a one-day programme for applicants, which provided a smoother transition from school/college to university, and specifically addressed anxieties around starting university and to explore the support available at GCU. 3 -Continue to develop GCU Summer Transitions workshops The Disability Team, in partnership with the National Autistic Society (Scotland), delivered a Summer Transition Programme for applicants with a diagnosis on the autism spectrum (or Asperger’s syndrome). 4 - Embed module on Mental Health and Wellbeing on GCU Learn The GCU Wellbeing Team launched their mental Health and Wellbeing Module on GCU Learn in April 2020. 5 - Explore the possibility of a Mindfulness module at GCU This module was introduced and embedded as part of the Mental Health and Wellbeing module on GCU Learn. 6 - Scottish Mental Health First Aid training was offered to students taking part on the Student Leadership Programme in trimester A and B at the Students' Association. Due to Covid-19 lockdown Tri B sessions were stalled but will be completed on Zoom. | 1 - Continue to offer free Mindfulness course The mindfulness course has been offered to GCU students both in person and online throughout the first and second trimester. The course in the first trimester was well attended, with an established waiting list for students who were keen to attend the sessions. The second trimester mindfulness provision has been offered online through the Mental Health and Wellbeing Module. The Module overall has been evaluated in this document, but specifically in regards to the mindfulness provision, the GCU Wellbeing Team have established a Facebook event for this which has reached 2,200 individuals. Despite this offering, the sessions have had low attendance with our students, and we are currently working to enhance the student engagement with these sessions. 2 - Offering Mental Health Matters workshop at Inductions This workshop was offered for the first time last summer after identifying a need for more specific pre-entry support for students who disclosed a mental health condition. This was a pilot programme and students who attended were encouraged to provide feedback on the sessions. 3 -Continue to develop GCU Summer Transitions workshops Our Summer Transitions Programme has been running since 2010, and has seen a steady increase in attendance each year. We have adapted the programme over time to ensure it meets the needs of those who attend, and is relevant and current to our students. 4 - Embed module on Mental Health and Wellbeing on GCU Learn The GCU Wellbeing Team have worked to put together an online platform where self-care information, wellbeing resources, and our usual trimester workshops can be engaged with by students from home. This had been in development throughout the academic year, but was launched in April 2020 and has been particularly impactful during the Covid-19 Pandemic. The module allows the wellbeing team to deliver live (and record) workshops on Mindfulness, engage students with self-care resources, online podcasts and more. 5 - Explore the possibility of a Mindfulness module at GCU When the Student Wellbeing Team explored our VLE provider, we discovered it was possible to introduce a variety of different tabs and learning sessions in the one platform, meaning we no longer would have to develop an independent mindfulness module, and another for broader wellbeing courses. This meant we were able to combine the mindfulness into this provision, and have evaluated the action under this area. This module was introduced and embedded as part of the Mental Health and Wellbeing module on GCU Learn. 6 - Training was very useful on a personal level as well as within the university and was put to use immediately and several times since. Have used the training on 3 students within the university and one person external to the university. The training allows you to ask difficult questions. Continue with training for next year. | 1 - Continue to offer free Mindfulness course Whilst the delivery of the mindfulness course on campus has been well attended and received, the online provision of the workshops was engaged with to a lesser extent by our students. We are currently exploring avenues to increase this engagement, and will continue to offer the mindfulness sessions in the upcoming academic year. 2 - Offering Mental Health Matters workshop at Inductions 15 Students were able to attend the induction workshop, and feedback showed the workshop was overall positively received. Students appreciated the opportunity to visit campus and speak to staff before starting university. Some felt the session was too long, some too short! This year, we have had to adapt very quickly to delivering pre entry programmes remotely, and are in the progress of re-designing MHM for delivery online. Our challenge is again student engagement, and ensuring our pre entry programmes are inclusive and accessible. 3 -Continue to develop GCU Summer Transitions workshops We use student feedback and sector wide knowledge to shape our transitions programme, and review this yearly. We have involved current autistic students in the programme more in recent years, which has been very much needed and makes a really positive impact on those attending. Again, this year we face the challenge of adapting this 3-day programme to an online version that students can engage with. 4 - Embed module on Mental Health and Wellbeing on GCU Learn Since launching to students on the 20th of April, there has overall been 924 hits to the module page, which has an evenly distributed cluster between 10am and 7pm, but seems to be disproportionally accessed during the weekdays rather than at weekends. The newsletter issue which has been used to engage students with the module and provides instructions on how to enrol and access this was sent to 339 individuals, of which there has been a total of 290 opens. The module also features a section in which we have included an embedded Padlet and the contact details of the course co-ordinator to engage students with co-creating the content of the module and gathering feedback on what support we could enhance the module to provide to enhance their wellbeing. 5 - Explore the possibility of a Mindfulness module at GCU This module was introduced and embedded as part of the Mental Health and Wellbeing module on GCU Learn. Impact of the Mindfulness sessions is explored under action 1 of Workshops. 6 - The Scottish Mental Health First Aid course was available to students on the SA Student Leaders Programme in both trimesters this year again. In the first trimester 12 students completed the training and in trimester 2 there are 15 students who started it before lockdown and will complete it via Zoom soon. So 27 students trained subject to Zoom sessions being completed. The impact of this should be more capable student peer supporters on campus and in the community and student leaders with a good understanding of mental health issues.
5 - Supporting Specific Student Groups | 1 - Campus Quiet Spaces promotion 2 - Continue offering a Social Meet Up group 3 - Establish a Time4You Group for Student Carers 4 - Working in partnership to co-create a Mental Health Related Sports Club at GCU Students’ Association. 5 - Continue the Active Minds Referral Scheme 6 - Continue the Social Eyes Programme | 1 - Creation of a new quiet room/calm zone at GCU Students’ Association as a safe calm space available for all students; the start of of creating a video from Full time officer lead to highlight quiet spaces and downloadable map highlighting this and other currently available quiet spaces on campus and how to find them. The Student Wellbeing Team worked to highlight the quiet spaces available for GCU students throughout the academic year. A specific leaflet was established outlining quiet spaces and routes for students at the GCU Freshers’ Fayre, and there has been an ongoing project to enhance the quiet space provision across the GCU Glasgow Campus by working in partnership to identify additional quiet spaces, establish a map which outlines these areas, and communicate these to students. 2- The Student Wellbeing Service are evaluating their social meet up group after delivering it in Trimester A of the 19/20 Academic year, which is an informal weekly meet-up group for students to take some time out to focus on their health and wellbeing. 3 - A Time4You group was set up by the SA Student Carer Officer with a private a Facebook page. They ran a couple of social support groups throughout Trimester A and have also had a few stalls at different university events/days in partnership with the wellbeing team. 4 - Although discussions took place on this at the start of the year between the SA and GCU Wellbeing progress on this action has not been made this year. 5- referred for a discounted (or sometimes free for the student) gym membership to engage with physical activity through using the campus gym or classes to benefit their mental wellbeing. 6 - The Disability Team run a Social eyes programme for GCU students who have a diagnosis, or who would identify with a diagnosis, on the autism spectrum. ‘Socialeyes’ is a programme developed by the National Autistic Society to facilitate social skills and social understanding for people on the autism spectrum. | 1 -Quiet spaces are what students want and have asked for. The quiet space at the Students' Association was welcomed by students and work is ongoing to identify additional areas across the University campus to establish quiet spaces in. This is to compliment the pre-existing map of these spaces for students which was published at Fresher's', and pop up calm zones have received positive feedback from students when they were present at events. 2 -The Social Meet up Group was offered to GCU Students throughout the first trimester of the 2020/2021 Academic year. Although the group in previous years has seen a great uptake for students, this year there were declining numbers despite engaging student groups and societies to host sessions for the weeks. The sessions were postponed during the first trimester with the intention of re-evaluating and relaunching the groups in the second trimester. 3 - This group has been set up and private social media group established. Needs refreshed for next year. 4 - Whilst the Active Minds referral scheme to exercise classes at the Arc Gym on campus is administered by staff in the Wellbeing team who refer individual students, this club requires active student involvement in setting up and running and individuals interested in doing this were not identified this year. It's addition to a future plan should be based on a clear desire from students to be involved in the set up and running of such a club. 5 - Continue the Active Minds Referral Scheme This programme has run for a number of years and has continued to be offered and utilised by students, and has received positive reviews. We aim to continue this provision throughout the following academic years. 6 - Continue the Social Eyes Programme The social eyes programme has been under review for the first and second trimesters with NAS to help redevelop the content of the programme and engage students. | 1 - A new SA quiet room was created at the Students' Association - this previously underused room that was used by liberation groups was cleared out, painted and decorated to provide a calming quiet space available for any students to use. Existing quiet spaces on campus were highlighted within Mindful Monday social media posts along with this new space. Work began on a video and online map for Quiet Space on campus but this has stalled since the Covid-19 lockdown. This will be picked up once we are back on campus in 2020-21. Additionally, the group who were working to identify new quiet spaces across the campus has postponed this area of work until a return to campus can be made. This is because the group aim to undertake student and staff consultation on the areas and uses before implementing these. 2 -The group is being redeveloped and will be relaunched once this has been completed. The development of a schedule and evaluation of the group was impacted and postponed due to Covid-19 as this required the active involvement of students and student groups. 3 - Whilst a group was set up by the part time officer it has not been possible to get meaningful data on number of meetings/participants or their feedback on this. This will be a priority for improvement in future. 4 - This action was not achieved. As reflected in the earlier section this was in part due to a lack of student will for this project, or from it not coming from a genuine need expressed by students. It is not likely to be included in future plans without consultation with students and active interest from them in taking this forward. 5 - Continue the Active Minds Referral Scheme The programme has had less referrals this academic year due to the closure of the campus in the middle of the second trimester as a result of Covid-19. Overall the programme is well received by students and will continue to be offered. 6 - Continue the Social Eyes Programme The social eyes programme continues to be refined and developed, and is aimed to be launched for the upcoming academic year.
6 - Promotion of Student Services | 1 - Promotion of GCU Students' Association and GCU Wellbeing Team services 2 - Start work towards creating a large Peer to Peer Support Network 3 - Mental Health First Responder Scheme Pilot 4 - Work to establish a self-help resource list at the GCU library 5 - Continue to be involved in GCU Student Services Fairs 6- Develop and enhance support resources for the GCU Wellbeing Team 7 - Launch a Wellbeing Newsletter within the GCU Wellbeing Service | 1 - Fortnightly promotion of the Advice Centre and Nightline has taken place to all students via the GCU Students' Association all student email and regular social media posts (at least fortnightly); Screen adverts around campus have carried updated Advice Centre and Nightline e-poster campaigns; Advice Centre and Nightline stalls were present and giving out freebies and info/recruiting volunteers at the Fresher's and refreshers fayres in September and January; Stall also advertising Advice Centre and Nightline as part of exam stress campaign at SA and during Nightline Awareness week in November. The GCU Wellbeing Team have worked to promote their service and engage students with their health and wellbeing throughout the academic year. This has included establishing and introducing a weekly wellbeing newsletter for our students, redeveloping all our student wellbeing webpages (including also the wellbeing pages for our GCU London campus), working with students to develop a campaign and more. The Mental Health and Wellbeing Group at The Students' Association promoted all events and shared posts from SA , Full Time Officers, Glasgow Caledonian University and Wellbeing team. 2 - Project scoping undertaken with reference to similar 3 year projects already started at other institutions. Application for lottery funding scheduled to be completed by end May to enable roll out over several years of "Mind You Mate" training at GCU starting from 2020-21 academic year. 3 - Application for Think Positive Small Grant successful; purchase of lanyards; working with GCU partners to establish role definition and which staff members to be approached to take part; working with GCU Wellbeing and SAMH to deliver training. Pilot now planned for 2020-21 term once training can be delivered over summer 2020 (this was plan before Covid-19). 4 - Work to establish a self-help resource list at the GCU library The GCU Wellbeing Team has worked with the Sir Alex Ferguson Library to create a GCU wellbeing resource list. The list has books and eBooks which are available online, alongside videos and other resources. 5 - Continue to be involved in GCU Student Services Fairs The GCU Wellbeing Team has worked with colleagues across the University to be involved with the Student Services fairs, which are held each academic trimester and aim to engage students with the internal support available to them to enhance their student experience - this includes the VISA team, Careers, Student Events, Students’ Association and more. 6- Develop and enhance support resources for the GCU Wellbeing Team To help increase awareness and engagement by staff and students of the available wellbeing resources from the GCU Wellbeing Team, this year we enhanced our existing, and developed some new wellbeing resources. This included an information leaflet for parents and carers of new students, redeveloping our carers leaflet, a new leaflet for the service, and redesigning our Identifying and Supporting Students in Distress Guide. Further information on this can be found in the Supporting Staff Section. 7 - Launch a Wellbeing Newsletter within the GCU Wellbeing Service To engage students with the service and help enhance their understanding of self-care, mental health and the support available to them both from GCU and in their local community, the GCU wellbeing service established a Wellbeing Newsletter. This was launched in September 2020 and currently has 483 contacts, 352 of whom are subscribers. | 1 - The Students' Association Communications strategy for promoting our Advice Centre, Nightline and University Wellbeing services has gone well. It might be that due to Covid-19 and a probable move to online only services for the foreseeable future that this will need to be revised for next academic year. Throughout the academic year the team has been visible both across campus and through electronic engagement with our student and staff communities. Several new approaches, including establishing an Instagram, newsletter, and redeveloping our webpages have been particularly impactful in our online engagement. 2 - Application guidelines from other HE institutions has been gathered and meetings had been arranged to discuss. The application had been outlined and was due to be written end of March/April. This was put on hold due to COVID-19 and will be re-established 2020/2021 by one of the Full time officers. 3 - Initially the lanyard scheme was for the university and SA staff to signpost students, however discussions with the university and the SA highlighted issues with students' expectations and it was decided that staff would receive SAMH training before they wore the lanyards. As SAMH would not be delivering training until summer 2020 it was decided the scheme would wait until start of term 2020/2021. 4 - Work to establish a self-help resource list at the GCU library The Wellbeing resource list published with the GCU Sir Alex Ferguson Library has helped to pull the current internal and external provisions GCU students have access to in one place - for example self-care books and eBooks. 5 - Continue to be involved in GCU Student Services Fairs The wellbeing team were present at both days of the fairs on the 15th and 17th of October. Although no official measures were recorded - the team were able to engage with and pass resources to a number of students over the two days about internal and local support services available to them. 6- Develop and enhance support resources for the GCU Wellbeing Team In September we launched our new leaflets with information for the parents and carers for new students at GCU. The aim of this leaflet was to engage the social communities of individuals around our students in thinking about how they can speak with the student about engaging with existing support structures in the university to enhance their wellbeing. The leaflet also outlines the confidentiality of services and information sharing, and what to do if they have concerns about the student. We have also published a refreshed leaflet of the student carers information, which includes resources provided by the Students’ Association and local services, alongside our identifying and supporting students in distress guide which is expanded on further below in our staff section. Finally, we are still working to develop a new leaflet for the overall wellbeing service which will be published and launched physically on return to campus, and online as soon as this has been finalised. 7 - Launch a Wellbeing Newsletter within the GCU Wellbeing Service The newsletter is sent out weekly to GCU Students, and a number of different days and times have been trialled to ensure optimum engagement with our student body. Students (and others) have the opportunity to shape the content of the newsletters and are encouraged in each issue to reach out to the wellbeing team with suggestions for content. | 1 - All regular communications were completed for Advice Centre and Nightline services. Numbers accessing the Advice Centre by the end of trimester 2 (when we were in lockdown and had also reduced staff hours from 91 to 77 per week) remained similar to the previous year at this point (841 this year for one off enquiries compared to 850 last year). This means that despite reduced access due to lockdown and reduced staffing students were still kept aware of our services. The Nightline service has been closed since March 13th due to Covid - 19 and has had a lot of technical difficulties that impacted on call numbers in trimester 1 surrounding an office move and BT phone line problems. Contacts (phone, online and texts) were significantly lower than the previous 2 years in both trimesters due to this despite regularly social media and Awareness week campaigns to keep awareness of the service high Amongst students. By working to promote the wellbeing service throughout the year we have been able to work to engage students across a variety of new platforms, including social media platforms such as Instagram. Due to covd-19 we are unable to compare year on year at this time. 2 - Research and scoping as to the potential shape of project has been undertaken by the Chief Executive of the SA and the FTO; lottery funding on the basis of this will be applied for over the summer though probably roll out of the project (initially planned for 2020-21) will need to be postponed due to continued Covid-19 restrictions. 3 - The Students' Association were successfully in being granted funding for the project from Think Positive Small Grants. FTO has been liaising with university stakeholders to identify staff to approach to take part as Mental Health First Responders (lanyard wearers) and to define the role of lanyard wearers. SAMH training was identified for staff and was planned for summer 2020 prior to Covid-19 lockdown. The pilot launch will also need to be postponed due to Covid-19. 4 - Work to establish a self-help resource list at the GCU library An impactful outcome from the resource list was the development of the idea to establish a wellbeing area in the GCU Sir Alex Ferguson Library. Consultation for this idea with our students and staff has been undertaken on University Mental Health Day (and electronically beyond this) - and a working group occurs in the University to shape the idea moving forward. This has also resulted in the further development and investment in the on campus and online self-care provision available to GCU Students. 5 - Continue to be involved in GCU Student Services Fairs The Student Wellbeing Service has continued to be involved in the student services fair which has provided an additional opportunity to engage with students across the university. 6- Develop and enhance support resources for the GCU Wellbeing Team The new resources have enabled an enhanced presence from the wellbeing team across events in the University – including having a stall at Open Days to engage with the parents and carers and potential students. By redeveloping our Identifying and Supporting students in distress guide we have been able to actively engage the needs of our academic staff, and work to provide a clear structure of their roles, pastoral support, and in what circumstances to signpost. 7 - Launch a Wellbeing Newsletter within the GCU Wellbeing Service The newsletter alongside offering a valuable place for the wellbeing team to engage with students regularly, has also allowed the team to produce standalone webpages to help communicate with a wider audience. This has been particularly impactful in the student wellbeing module - in which the launch newsletter has been used as a webpage to help direct students to the resource and provide enrolment instructions. All issues to the newsletter can be viewed here.
7 - Staff Support | 1 - Launching the staff mental health resources area on internal webpages 2 - Identifying and Supporting Students in Distress handbook 3 - Continue the Mental Health at Work Taskforce 4 - Continue the Mental Health at Work Action plan | 1 - Launching the staff mental health resources area on internal webpages To enhance the awareness of our GCU Staff community of the available support for their health and wellbeing, we worked to develop and launch an internal resource area on our intranet (Caledonian Connected). The webpages highlight available resources, training, services, supporting students, support for managers, events and more. 2 - Identifying and Supporting Students in Distress handbook The GCU Wellbeing Team redeveloped a range of our resources, including the resources to help staff identify and support students in distress. The aim of this redeveloped was to combine our flowchart and document resources into one handbook which is easily accessible to GCU Staff, and enhance awareness of how to support GCU Students. The information was also contextualised to GCU Support Sources. 3 - Continue the Mental Health at Work Taskforce The Mental Health at Work Taskforce is a committee within GCU which has oversite of the Mental Health at Work Action Plan. The groups work is fed into other areas of work across the University, including the Student Wellbeing Advisory Group, and has representation from across the University Community. The taskforce has continued to operate this year. 4 - Continue the Mental Health at Work Action plan In 2019, GCU introduced the development of a Mental Health at Work Action Plan. Throughout the year GCU continued to enhance this action plan and further develop the ongoing work to support staff mental health. The action plan is overseen by the Mental Health at Work Taskforce. | 1 - Launching the staff mental health resources area on internal webpages In collaboration with the student wellbeing team, staff across the University and the Associate Vice Principal Health and Wellbeing, a new resource was established for GCU’s internal webpages for staff mental health and wellbeing. 2 - Identifying and Supporting Students in Distress handbook The redeveloped of the Identifying and Supporting students in distress handbook has enabled two previous documents to be merged with contextualised support resources for GCU students both on campus, in the local community and out of hours. It helps to educate academic staff on how they can support students with their wellbeing, what to do if they have concerns, and at what point how they can signpost to appropriate support. This has been a welcomed resource from staff, and the ability to order more booklets for individual departments and events has also been well received. 3 - Continue the Mental Health at Work Taskforce The Mental Health at Work Taskforce has been able to continue to provide a cross institutional approach for the enhancement of staff wellbeing at GCU. 4 - Continue the Mental Health at Work Action plan The Mental Health at Work Action Plan has enabled a central point to provide a cross institutional approach for the enhancement of staff wellbeing at GCU by looking at various operational and strategy actions. | 1 - Launching the staff mental health resources area on internal webpages The resources have been well received by staff, and enable a centralised point for support information, self-care provisions, services and more to be communicated, alongside one place where staff can search and direct to this information. The resources also featured mental health training (both online and upcoming live sessions for staff) which has been well received by staff. Our on campus training sessions have been fully booked, with waiting lists being established. 2 - Identifying and Supporting Students in Distress handbook The booklet has been well received and an impactful outcome is the further development of staff sessions to go through the booklet and process with academic staff and address any concerns they may have. These are in development and will be launched for the next academic year. The booklet is also in the process of being further developed and contextualised for our GCU London campus. 3 - Continue the Mental Health at Work Taskforce The Mental Health at Work Taskforce has been able to continue to provide a cross institutional approach for the enhancement of staff wellbeing at GCU. This has been well received, and all impact measures have been achieved. This will be continued into the next academic year. 4 - Continue the Mental Health at Work Action plan The Mental Health at Work Action Plan has had a series of impact outcomes, including the development and introduction of the previously referenced Staff Mental Health Webpages, and the introduction of a suite of mental health awareness training for all GCU Staff.
Your overall experience of taking part in the project: Our overall experience in taking part in the project has been positive. From the launch in Edinburgh last year there has been a good level of support and resources available from NUS Think Positive team making the whole process straight forward. In particular having the final reporting spreadsheet was a good idea to avoid the production of overly long documents. The circumstances around lockdown from Covid-19 have made things a lot less straight forward, particularly in finishing off actions that were physically based or involved being on campus, and in some cases having access to paper based outputs such as attendance lists for activities etc. Covid-19 will definitely give a new focus on working out how to ensure that student mental health is prioritised across the whole institution in the remote learning model that we will have for the foreseeable future.
What can Think Positive do to further support you with this work: Think Positive have provided the right amount of support, with online documents, check lists and further help always available if needed. Perhaps it could be useful to see examples of the variety of SMHAs that have been produced over the past years of the project but this was to an extent already provided at the launch from the speakers there. It would be helpful to issue the Impact Document Template, and guidance for the Student Mental Health Agreement at the beginning of the year, so that data can be gathered which is relevant to the impact document (as I had to spend a lot of time reorganising what I had collected throughout the year with the new outline).
Any other comments: The spreadsheet is quite difficult to navigate and I feel this could be amended to an online workbook (NUS have a platform they use for Green Impact which was really simple and I think would be easier, and also allows for multiple contributions in one platform at the same time). The spreadsheet also loses some key functionality which in prior Impact Reports have been helpful in terms of demonstrating event impact (for example being able to re-direct to webpages, include images from events, etc.)